Year at a Glance

GOALS:

| Tasks | Events  |
| --- | --- |
| **June** | * 1 – Identify assessment /curriculum alignment team
* 1 – Develop interim assessment calendar
 |  |
| **July** | * 1 –
* 2 – Review interim assessments to determine if revision/development is needed
* 2 – Align curriculum scope & sequences with interim assessments
* 3 –
* 4 –
 |  |
| **August** | * 1 –
* 2 –
* 3 – Deliver PD based on School Improvement Plan developed in May
* 4 – First week of school
 | Back to School Night  |
| **September** | * 1 – Quarterly leadership Team meeting
* 2 – Distribute interim assessment #1 to teachers for planning
* 2 – Develop plans for scoring and analysis of interim assessments
* 3 – Deliver PD (if necessary) on data analysis to instructional leaders
* 4 – PBIS recognition
 |  |
| **October** | * 1 – Conduct focused walkthrough with instructional leaders
* 2 – Interim assessment #1
* 2 – Analyze evidence gathered in week 1 walkthroughs, plan PD
* 3 – Observe data analysis meetings
* 4 – Deliver PD based on evidence gathered in walkthroughs and School Improvement Plan goals
 |  |
| **November** | * 1 – Distribute interim assessment #2 to teachers for planning
* 1 – Review IA #1 data with staff, predict student performance on IA#2
* 2 –
* 3 – PBIS recognition
* 4 – Parent Conferences/Thanksgiving Holiday
 | Food drive  |
| **December** | * 1 – interim assessment #2
* 1 – Conduct focused walkthrough with instructional leaders
* 2 – Observe interim assessment analysis meetings
* 2 – analyze evidence gathered in week 1 walkthroughs, plan PD
* 3 – Quarterly leadership team meeting
* 3 – Deliver PD based on evidence gathered in walkthroughs and School Improvement Plan goals
* 4 – Winter Break
 |  |
| **January** | * 1 – Distribute interim assessment #3 to teachers for planning
* 1 – Review IA #2 data with staff, predict student performance on IA #3
* 2 – Conduct focused walkthrough with instructional leaders
* 2 – Analyze evidence gathered in week 1 walkthroughs, plan PD
* 3 – Deliver PD based on evidence gathered in walkthroughs and School Improvement Plan goals
* 4 –
 | Mid-Year Evaluations DueSemester grades |
| **February** | * 1 – Conduct focused walkthrough with instructional leaders
* 2 – interim assessment #3
* 2 – Evaluate evidence gathered in week 1 walkthroughs, plan PD
* 3 – Observe data analysis meetings
* 4 – Deliver PD based on evidence gathered in walkthroughs and School Improvement Plan goals
 |  |
| **March** | * 1 – Conduct focused walkthrough with instructional leaders
* 2 – Observe interim assessment analysis meeting
* 2 – Plan PD based on evidence gathered at walkthrough
* 3 – Review IA #3 data with staff, begin goal setting for next year
* 4 – PBIS recognition
 |  |
| **April** | * 1 – Spring Break
* 2 – Engage instructional leaders in School Improvement planning process
* 3 – Write draft School Improvement Plan and create process for approval at leadership team meeting
 | State testing |
| **May** | * 2 – Quarterly leadership team meeting
* 4 – End of year staff celebration
 | Teacher Evaluations Due |